## Project schedule
| SafeRoute Logistics: An Intelligent Fleet | [5 empty] | Project start: | [7 empty] | 2026-02-09
| System | [5 empty] | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-09 to 2026-04-05
 | time axis 2026-02-09 to 2026-04-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning Phase (D00)
| Group Formation & Idea Discussion | SN Mbhalati, Magubane SX, Motsokoane MI and TC Shongwe | 100% | 2026-02-09 | 2026-02-18 | 10
| Group Registration | SN Mbhalati | 100% | 2026-02-09 | 2026-02-18 | 10
| Project Proposal Development | SN Mbhalati, Magubane SX, Motsokoane MI and TC Shongwe | 100% | 2026-02-19 | 2026-03-18 | 28
Analysis Phase (D01)
| Requirements Gathering & Analysis | Magubane SX | 100% | 2026-03-19 | 2026-03-27 | 9
| Feasability and Risk Study | SN Mbhalati | 100% | 2026-03-19 | 2026-03-27 | 9
| Use Case Identification | Motsokoane MI | 100% | 2026-03-19 | 2026-03-27 | 9
| Problem Statement & Proposed Solution | TC Shongwe | 100% | 2026-03-19 | 2026-03-27 | 9
| Milestone: Deciding on the project topic |  |  | 2026-03-19
Design Phase (D02)
| Use Case Descriptions | SN Mbhalati | 100% | 2026-03-28 | 2026-04-24 | 28
| Activity Diagram Development | SN Mbhalati, Motsokoane MI and TC Shongwe | 100% | 2026-03-28 | 2026-04-24 | 28
| Functional & Non-Functional Requirement Updates | Magubane SX | 100% | 2026-03-28 | 2026-05-22 | 56
| Use Case Diagram Corrections | Motsokoane MI and TC Shongwe | 100% | 2026-03-28 | 2026-05-22 | 56
| MVP & Core Feature Refinement | Motsokoane MI | 100% | 2026-03-28 | 2026-05-22
| Iterative Prototype Development | SN Mbhalati, Magubane SX and TC Shongwe | 20% | 2026-03-28 | 2026-04-24 | 28
System Design Phase (D03)
| Updates Required | SN Mbhalati, Magubane SX, Motsokoane MI and TC Shongwe | 100% | 2026-04-25 | 2026-05-08 | 14
| Database Design | Motsokoane MI and TC Shongwe | 100% | 2026-04-25 | 2026-05-08 | 14
| Class Diagram Development | Motsokoane MI | 100% | 2026-04-25 | 2026-05-08 | 14
| Interaction Sequence Diagrams | Magubane SX and Motsokoane MI | 100% | 2026-04-25 | 2026-05-08 | 14
| Authentication MVP Database Integration | SN Mbhalati | 100% | 2026-04-25 | 2026-05-08 | 14
| Prototype Improvement | SN Mbhalati, Magubane SX and TC Shongwe | 40% | 2026-04-25 | 2026-05-08
Architecture & Validation Phase (D04)
| Updates Required | Magubane SX, Motsokoane MI and TC Shongwe | 100% | 2026-05-09 | 2026-05-22
| Component & Deployment Diagram | SN Mbhalati | 100% | 2026-05-09 | 2026-05-22
| Gantt Chart Development | Motsokoane MI | 100% | 2026-05-09 | 2026-05-22
| Activity & Sequence Diagram Refinement | Magubane SX and Motsokoane M | 100% | 2026-05-09 | 2026-05-22
| Crime Hotspot MVP Integration | SN Mbhalati and TC Shongwe | 100% | 2026-05-09 | 2026-05-22
| Alpha Prototype Preparation | SN Mbhalati and TC Shongwe | 70% | 2026-05-09 | 2026-05-22
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.